## Sheet1
| Th W3D4 | Fri W3D5 | Saturday | Sunday | Mon W4D1 | Tues W4D2 | Weds W4D3 | Thurs W4D4 | Fri W4D5
Planning | Planning and Prep
Prototype |  | Prototype
Features |  |  |  |  | DB and CRUD
API
Sockets
Deployment | [5 empty] | Add to GIT |  | Push to GIT
Presentation | [8 empty] | Present